## Test Plan
Test ID | Test Case | Description | Expected Result | First Date Implement | Other Date Implement | Status | Remarks
Test01 | CSV Reading | reading from the csv | Successful to read csv | 2023-10-31 | 2023-11-01 | Pass
Test02 | Socket Test (one way communication) | Sending "hello world" via socket communication between server and client | "hello world" show at server/listener | 2023-11-01 | 2023-11-02 | Pass
Test03 | Socket Test (Two way communication) | Sending "hello server" and get reply "hello client" from server | "hello server" show at client/listener and "hello client" show at client cmd prompt | 2023-11-01 | 2023-11-02 | Pass
Test04 | Socket Test (multiple nessage) | Sending multiple time with one connection | two message been recveived accordingly | 2023-11-01 | 2023-11-02 | Fail | Found out that CPP need to reconnect for second message sending
Test05 | Socket Test (multiple access) | Multiple application connect to server | 3 cmd prompt can connect and received reply from server | 2023-11-01 | 2023-11-02 | Pass | Even there is connect from different cmd it was able to view and communicate with server
Test06 | Socket Test (large amount receiving) | Server receive large amount of message from client | 3 cmd prompt can connect and send request (eg: view stock, buy stock, sell stock) and still reply from server | 2023-11-01 | 2023-11-02 | Fail | Due to 1024 bit restriction of socket
Test07 | Socket Test (large amount sending) | Server send large amount of message | 3 cmd prompt can connect and send request (eg: view stock, buy stock, sell stock) and still reply from server | 2023-11-01 | 2023-11-02 | Fail | Due to 1024 bit restriction of socket
Test08 | Socket Test (requirement) | client view the stock detail | client send command 1 to the server | 2023-11-02 | 2023-11-03 | Pass | by press 1 client able to see the stock detail
Test09 | Socket Test (requirement) | client want to buy order via socket | client send command 2 and stock symbol, stock quantity and stock priceto the server | 2023-11-02 | 2023-11-03 | Pass | by press 2 client able to send the stock (symbol, quantity, price) to server and server will takes in as parameter
Test10 | Socket Test (requirement) | client want to sell order via socket | client send command 3 and stock symbol, stock quantity and stock priceto the server | 2023-11-02 | 2023-11-03 | Pass | by press 3 client able to send the stock (symbol, quantity, price) to server and server will takes in as parameter
Formulas:
First Date Implement = [First Date Implement, row above]
Other Date Implement = [Other Date Implement, row above]